## Sheet1
Project Name: | Marketing Strategy for RAIL-D
Project Manager: | Jaiden Angeles, Emily Chan, Yuling Dai, Daisy Huynh, James Lee, Tianci Qiao
Date: | October 14, 2022
Sponsor: | Simran Gill, Principal of Bridgemark Management
Gantt Chart
Task | Start Date | Time | End Date included weekend
Task 1.1.1 Determine industry needs through surveys | 2022-10-11 | 14 | 2022-10-24
Task 1.1.2 Identifying 2-3 profitable industries | 2022-10-25 | 7 | 2022-10-31
Task 1.2.1 Feasibility Analysis | 2022-11-01 | 7 | 2022-11-07
Task 1.2.2 Market Strategy | 2022-11-08 | 7 | 2022-11-14
Task 1.3.1 Profitable industry recommendation | 2022-11-15 | 11 | 2022-11-25
Task 1.3.2 Draft Pamhplet for most profitable industry | 2022-11-26 | 7 | 2022-12-02
Task 1.3.3 Final marketing pamplet | 2022-12-03 | 4 | 2022-12-06
Formulas:
End Date included weekend = [Start Date]+[Time]-1
Start Date = [End Date included weekend, row above]+1