## Sheet1
| Upass (4 months) | 176.8 |  |  |  | Total gas James need | 1.6198
| Upass (per day) | 1.4733 |  |  |  | Gas cost per lecture | 3.9361
| Day pass adult | 11
| Paper subcription cost per day | 89.95 | 0.24644
| Average gas price (July - Oct) | 2.43/litre
| Total kilometer for James | 18.2
| Averge gas per kilometer | 8.9L/100km | 0.089
| Minimum wage | 15.56
WBS | Task | Variable - Labor & gas | Fixed - Subcription & Upass | Times for travel | Work Hours | Number of people take public transportation | Days for each task | Budeget
1.1.1 | Determine industry needs through surveys | 124.5722 | 106.5835 | 2 | 7.5 | 5 | 14 | 231.1557
1.1.2 | Identifying 2-3 profitable industries | 1062.0161 | 53.2917 | 1 | 68 | 5 | 7 | 1115.3078
1.2.1 | Feasbility analysis | 221.7761 | 53.2917 | 1 | 14 | 5 | 7 | 275.0678
1.2.2 | Market Strategy | 338.4761 | 53.2917 | 1 | 21.5 | 5 | 7 | 391.7678
1.3.1 | Profitable industry recommendation | 147.9122 | 106.5835 | 2 | 9 | 5 | 14 | 254.4957
1.3.2 | Draft pamphlet for most profitable company | 268.4561 | 53.2917 | 1 | 17 | 5 | 7 | 321.7478
1.3.3 | Final marketing pamphlet | 50.6161 | 53.2917 | 1 | 3 | 5 | 7 | 103.9078
| Total Cost | 2213.825 | 479.6256 | 9 | 140 | 35 | 63 | 2693.4506